## Quality Control Template
Quality Control
Issue | Description | Imperfections | Identified By | To Be Fixed By | Priority | Status | Date Opened | Date Closed | Notes
Payment Gateway | Payment not processing on certain debit cards | 6 | Ahmed | Nour | High | Open | 2025-04-12 |  | Linked to third-party API issue
Menu Rendering | Items not loading properly on slow connections | 8 | Rawan | Seif | Critical | Open | 2025-04-13 |  | Impacts user checkout experience
Order Tracking | Map not updating driver location in real-time | 4 | Sara | Ramy | Medium | Closed | 2025-04-06 | 2025-04-10 | Fixed with backend location update
UI Overlap | "Add to Cart" button overlaps footer in smaller screens | 3 | Ahmed | Mohamed | Medium | Open | 2025-04-15 |  | Appears only on iPhone SE 2020
Localization | Arabic translations missing for some key checkout labels | 7 | Nour | Seif | High | Open | 2025-04-16 |  | Impacts user trust in native language UX
Notification Bug | Push notifications not arriving for scheduled orders | 5 | Rawan | Ramy | Medium | Open | 2025-04-17 |  | Isolated to Android 11 devices
Login Errors | Social login via Apple sometimes returns null token | 2 | Ahmed | Mohamed | Low | Closed | 2025-04-02 | 2025-04-06 | Temporary workaround implemented
Inventory Sync | Restaurant out-of-stock updates not syncing with frontend | 9 | Sara | Nour | Critical | Open | 2025-04-18 |  | Causes false availability info to users
Delivery Radius | Users outside allowed radius still able to place orders | 6 | Rawan | Seif | High | Open | 2025-04-19 |  | Requires geolocation revalidation
Cart Duplication | Cart items duplicated after app resumes from background | 3 | Ahmed | Ramy | Medium | Closed | 2025-04-05 | 2025-04-08 | Caused by race condition in local cache
Installation Failure | App crashes on Android 13 during installation | 12 | Ahmed | Sara | Critical | Open | 2025-04-15 |  | Only occurs on Samsung Galaxy devices
Login Timeout | Login process hangs for over 10 seconds | 9 | Nour | Rawan | High | Open | 2025-04-12 |  | Backend latency suspected
Order Not Saved | Orders disappear from cart when app is minimized | 11 | Rawan | Ahmed | Critical | Open | 2025-04-13 |  | Session management issue
Misleading Labels | "Free Delivery" tag appears on non-eligible restaurants | 6 | Ahmed | Nour | Medium | Open | 2025-04-10 |  | Filtering logic to be updated
App Freezing | Freezes when user taps "Track Order" on some Android phones | 10 | Mostafa | Ramy | High | Open | 2025-04-16 |  | Possibly related to GPS access
Slow Loading | Restaurant list loads in 15+ seconds on poor networks | 7 | Sara | Rawan | Medium | Open | 2025-04-15 |  | Add lazy loading or skeleton UI
Payment Gateway Crash | App crashes after selecting PayPal | 9 | Nour | Ahmed | High | Open | 2025-04-11 |  | Only PayPal affected, not Stripe
Missing Images | Some restaurant images fail to load | 5 | Ahmed | Seif | Medium | Open | 2025-04-17 |  | CDN reliability issue
Incorrect Totals | Checkout page shows wrong total with discounts | 8 | Rawan | Sara | High | Open | 2025-04-13 |  | Coupon logic needs review
Address Auto-fill Error | Address fields reset after selection | 4 | Seif | Ahmed | Medium | Open | 2025-04-16 |  | Google Maps API update needed
Driver Assignment Fail | Orders stay unassigned for over 5 mins in some zones | 10 | Sara | Ramy | Critical | Open | 2025-04-12 |  | Dispatch system under load
UI Glitch - iOS | Bottom nav bar overlaps content on iPhone 14 | 6 | Rawan | Seif | Medium | Open | 2025-04-14 |  | CSS fix required
Wrong Restaurant Rating | Ratings shown belong to another vendor | 7 | Ahmed | Nour | High | Open | 2025-04-10 |  | Review aggregation bug
Notifications Missing | Push notifications not sent for delivered orders | 6 | Mostafa | Ramy | Medium | Open | 2025-04-12 |  | Firebase config to be checked
Favorites Not Saving | Tapping “Favorite” does not save the restaurant | 5 | Nour | Seif | Medium | Open | 2025-04-11 |  | Local storage inconsistency
Language Switch Failure | Language does not switch after selecting Arabic | 7 | Rawan | Ahmed | Medium | Open | 2025-04-17 |  | Locale caching issue
Delivery Time Wrong | Estimated delivery time does not update with traffic conditions | 6 | Sara | Ramy | Medium | Open | 2025-04-13 |  | Needs integration with Google Traffic API
Promo Code Invalid | Valid promo codes rejected on checkout | 9 | Ahmed | Nour | High | Open | 2025-04-10 |  | Backend validator mismatch
Feedback Not Saved | Users’ feedback disappears after submission | 4 | Seif | Sara | Medium | Open | 2025-04-12 |  | API fails silently
Search Not Returning | Restaurant search returns no results when it should | 5 | Nour | Ahmed | Medium | Open | 2025-04-15 |  | Keyword search logic broken
Order Duplication | Double orders triggered when button tapped twice quickly | 6 | Rawan | Ramy | High | Open | 2025-04-14 |  | Debounce logic missing
Logout Not Working | Logout button does nothing on some devices | 3 | Ahmed | Seif | Low | Open | 2025-04-11 |  | JS event not binding correctly
Item Out of Stock Error | Users can add items marked "Out of Stock" | 5 | Sara | Nour | Medium | Open | 2025-04-15 |  | Status not synced with backend
Email Confirmation Lost | Users not receiving account confirmation emails | 8 | Rawan | Ramy | High | Open | 2025-04-13 |  | SMTP settings review needed
Schedule Order Failure | Scheduled orders fail to submit at checkout | 6 | Nour | Ahmed | High | Open | 2025-04-10 |  | Cron job missing
Tracking Map Blank | Real-time tracking map shows no driver path | 7 | Ahmed | Ramy | Medium | Open | 2025-04-16 |  | GPS polled data not rendering
Reorder Broken | Reorder option loads incorrect order history | 4 | Seif | Sara | Medium | Open | 2025-04-17 |  | API parameters incorrect
App Exit on Review | App closes unexpectedly after submitting a review | 9 | Mostafa | Ahmed | High | Open | 2025-04-15 |  | Exception not caught in feedback form
Notification Too Late | “Your order is on the way” sent after order delivered | 6 | Nour | Ramy | Medium | Open | 2025-04-14 |  | Event timing issue
Vendor UI Sluggish | Restaurant admin portal takes long to load menu editor | 8 | Ahmed | Seif | Medium | Open | 2025-04-12 |  | Possible SQL optimization needed
Payment Double Charged | Users charged twice for same order | 10 | Rawan | Ramy | Critical | Open | 2025-04-11 |  | Stripe webhook firing twice
Unclear Error Messages | "Something went wrong" shown without explanation | 5 | Sara | Nour | Medium | Open | 2025-04-16 |  | User-friendly error messages needed
VoiceOver Accessibility | App not fully usable with iOS VoiceOver | 7 | Nour | Seif | High | Open | 2025-04-18 |  | Visually impaired users face navigation issues
Profile Photo Not Saving | Uploaded user profile photos disappear on refresh | 4 | Rawan | Ahmed | Medium | Open | 2025-04-18 |  | Likely a caching or file path error
Driver Late Notification | Drivers not notified when pickup is late | 6 | Sara | Ramy | High | Open | 2025-04-18 |  | Driver app alert system not consistent
Night Mode Contrast Issue | Text unreadable in dark mode | 3 | Mostafa | Nour | Medium | Open | 2025-04-18 |  | WCAG contrast check failed
Delivery Area Bug | App says “out of range” for locations that are covered | 5 | Ahmed | Seif | High | Open | 2025-04-18 |  | Geo-radius misconfigured
Driver Cancels Not Alerted | Customer not notified when driver cancels | 7 | Rawan | Ramy | High | Open | 2025-04-18 |  | Order gets stuck in unassigned status
Backend CPU Spikes | CPU usage spikes when more than 100 orders are processed | 9 | Sara | Ahmed | High | Open | 2025-04-18 |  | Performance profiling needed
Vendor Hours Ignored | Orders accepted when restaurant is marked as closed | 8 | Nour | Seif | Critical | Open | 2025-04-18 |  | Restaurant hours not enforced
User Flag Ignored | Inappropriate user reported but account remains active | 4 | Ahmed | Ramy | Medium | Open | 2025-04-18 |  | Moderation system not triggering review
“No Cutlery” Ignored | Option to exclude cutlery not respected in delivery | 2 | Mostafa | Rawan | Low | Open | 2025-04-18 |  | Driver instructions not passed through backend
Keyboard Covers Input | On Android, virtual keyboard hides message input field | 3 | Nour | Ahmed | Medium | Open | 2025-04-18 |  | UI layout adjustment needed
Refund Stuck in Pending | Refunds remain in “pending” status for over 3 days | 6 | Sara | Seif | High | Open | 2025-04-18 |  | Stripe API response not updating UI
Allergens Not Listed | Menu items missing allergen and dietary info | 7 | Rawan | Nour | High | Open | 2025-04-18 |  | Legal compliance risk
Account Deletion Fails | Users unable to delete accounts through settings | 5 | Ahmed | Ramy | Medium | Open | 2025-04-18 |  | Backend endpoint blocked
Duplicate Push Alerts | Same push notification sent multiple times | 3 | Seif | Ramy | Low | Open | 2025-04-18 |  | Likely due to retry loop misconfiguration